## Resource Allocation
Functionality/Service | Utilization | Type of Resource | Estimated Man Hours
Sign In Service Group
| 80% | Business Analyst | 10
| 80% | Technical Architect | 12
| 80% | Visual Designer | 12
| 100% | Front End Web Developer | 14
| 100% | Back End Web Developer | 20
| 40% | Product Owner | 4
| 70% | Scrum Master | 12
| 50% | Agile Coach | 8
| 100% | Interaction Designer/User Researcher/Usability Tester | 12
| 100% | Product Quality Accountability | 8
Total |  |  | 112
Person Profile Service Group
| 80% | Business Analyst | 12
| 80% | Technical Architect | 12
| 80% | Visual Designer | 12
| 100% | Front End Web Developer | 16
| 100% | Back End Web Developer | 24
| 40% | Product Owner | 8
| 80% | Scrum Master | 16
| 60% | Agile Coach | 10
| 100% | Interaction Designer/User Researcher/Usability Tester | 14
| 100% | Product Quality Accountability | 10
Total |  |  | 134
Message Service Group
| 70% | Business Analyst | 8
| 80% | Technical Architect | 10
| 80% | Visual Designer | 10
| 100% | Front End Web Developer | 10
| 100% | Back End Web Developer | 14
| 40% | Product Owner | 4
| 80% | Scrum Master | 10
| 60% | Agile Coach | 8
| 100% | Interaction Designer/User Researcher/Usability Tester | 12
| 100% | Product Quality Accountability | 6
Total |  |  | 92
Facility Search Service Group
| 70% | Business Analyst | 8
| 80% | Technical Architect | 10
| 80% | Visual Designer | 10
| 100% | Front End Web Developer | 12
| 100% | Back End Web Developer | 24
| 50% | Product Owner | 8
| 80% | Scrum Master | 12
| 60% | Agile Coach | 6
| 100% | Interaction Designer/User Researcher/Usability Tester | 16
| 100% | Product Quality Accountability | 6
Total |  |  | 112

## Burndown
Project | Functionality/Service | Release | Story | Task | Start | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Total
SafeKids | Sign In Service | 1 | Story 1.1 (Parent Registration and Sign In) | Task 1.1.1 (Parent Account Creation) | 40 | 8 | 8 | 8 | 8 | 8 | 40
SafeKids | Person Profile Service | 1 | Story 1.2 (Manage Parent Profile) | Task 1.2.1 (Create Parent Profile) | 20 | 8 | 4 | 4 | 4 | 0 | 20
SafeKids | Person Profile Service | 1 | Story 1.2 (Manage Parent Profile) | Task 1.2.2 (Upload Pictures) | 20 | 0 | 8 | 4 | 4 | 4 | 20
SafeKids | Facility Search Service | 1 | Story 1.4 (Search Facilities) | Task 1.4.1 (Search Facilities) | 50 | 8 | 8 | 12 | 12 | 10 | 50
SafeKids | Message Service | 1 | Story 1.5 (Manage Inbox) | Task 1.5.1 (Send Message to Case Worker) | 35 | 8 | 8 | 8 | 6 | 5 | 35
SafeKids | Message Service | 1 | Story 1.5 (Manage Inbox) | Task 1.5.2 (Send Message to Foster Parent) | 15 | 0 | 0 | 8 | 4 | 3 | 15
Total |  |  |  |  | 180 | 32 | 36 | 44 | 38 | 30 | 180
|  | Ideal - Remaining Effort in Ideal Work Hours |  |  | 180 | 144 | 108 | 72 | 36 | 0
|  | Actual - Remaining Effort in Ideal Work Hours |  |  | 180 | 148 | 112 | 68 | 30 | 0
SafeKids | Sign In Service | 2 | Story 1.1 (Parent Registration and Sign In) | Task 1.1.2 (Identity Verification) | 40 | 8 | 8 | 8 | 8 | 8 | 40
SafeKids | Sign In Service | 2 | Story 1.1 (Parent Registration and Sign In) | Task 1.1.3 (CAPTCHA Validation) | 12 | 8 | 4 | 0 | 0 | 0 | 12
SafeKids | Person Profile Service | 2 | Story 1.3 (Manage Child(ren) Profile) | Task 1.3.1 (Create Child(ren) Profile) | 40 | 8 | 8 | 8 | 8 | 8 | 40
SafeKids | Person Profile Service | 2 | Story 1.3 (Manage Child(ren) Profile) | Task 1.3.2 (Upload Pictures) | 12 | 0 | 8 | 4 | 0 | 0 | 12
SafeKids | Facility Search Service | 2 | Story 1.4 (Search Facilities) | Task 1.4.2 (Integrate with Google Map) | 62 | 8 | 12 | 16 | 14 | 12 | 62
SafeKids | Message Service | 2 | Story 1.5 (Manage Inbox) | Task 1.5.3 (Receive email from Case Worker) | 20 | 0 | 8 | 6 | 6 | 0 | 20
Total |  |  |  |  | 186 | 32 | 48 | 42 | 36 | 28 | 186
|  | Ideal - Remaining Effort in Ideal Work Hours |  |  | 186 | 148.8 | 111.6 | 74.4 | 37.2 | 0
|  | Actual - Remaining Effort in Ideal Work Hours |  |  | 186 | 154 | 106 | 64 | 28 | 0
SafeKids | Sign In Service | 3 | Story 1.1 (Parent Registration and Sign In) | Task 1.1.2 (Change Password) | 20 | 8 | 6 | 6 | 0 | 0 | 20
SafeKids | Person Profile Service | 3 | Story 1.2 (Manage Parent Profile) | Task 1.3.3 (Edit Profile) | 10 | 0 | 6 | 4 |  |  | 10
SafeKids | Person Profile Service | 3 | Story 1.3 (Manage Child(ren) Profile) | Task 1.3.3 (Edit Profile) | 12 |  | 0 | 8 | 4 |  | 12
SafeKids | Person Profile Service | 3 | Story 1.3 (Manage Child(ren) Profile) | Task 1.3.4 (Upload Supporting Documents) | 20 |  | 8 | 6 | 6 |  | 20
SafeKids | Message Service | 3 | Story 1.5 (Manage Inbox) | Task 1.5.4 (Manage Inbox) | 22 | 0 | 0 | 8 | 8 | 6 | 22
Total | Total |  |  |  | 84 | 8 | 20 | 32 | 18 | 6 | 84
|  | Ideal - Remaining Effort in Ideal Work Hours |  |  | 84 | 67.2 | 50.4 | 33.6 | 16.8 | 0
|  | Actual - Remaining Effort in Ideal Work Hours |  |  | 84 | 76 | 56 | 24 | 6 | 0

## Burndown Charts
Actual Burndown
Ideal Burndown
Actual Burndown
Ideal Burndown
Actual Burndown